## 4.2
Progress
Month | 2017-01-30 | 2017-02-28 | 2017-03-30 | 2017-04-30 | 2017-05-30 | 2017-06-30 | 2017-07-30 | 2017-08-30 | 2017-09-30 | 2017-10-30 | 2017-11-30 | 2017-12-30 | 2018-01-30 | 2018-02-28 | 2018-03-30 | 2018-04-30 | 2018-05-30 | 2018-06-30 | 2018-07-30 | 2018-08-30 | 2018-09-30 | 2018-10-30 | 2018-11-30 | 2018-12-30 | 2019-01-30 | 2019-02-28 | 2019-03-30 | 2019-04-30 | 2019-05-30
Planned Prog | [12 empty] | 47% | 50% | 55% | 60% | 65% | 70% | 75% | 80% | 85% | 90% | 95% | 98% | 100%
Actual Prog | 2018-01-30: 14%; 2018-02-28: 17%; 2018-03-30: 20%; 2018-04-30: 23%; 2018-05-30: 26%; 2018-06-30: 30%; 2018-07-30: 55%; 2018-08-30: 60%; 2018-09-30: 65%; 2018-10-30: 70%; 2018-11-30: 72%; 2018-12-30: 75%; 2019-01-30: 80%
Cash In
Month | 2017-01-30 | 2017-02-28 | 2017-03-30 | 2017-04-30 | 2017-05-30 | 2017-06-30 | 2017-07-30 | 2017-08-30 | 2017-09-30 | 2017-10-30 | 2017-11-30 | 2017-12-30 | 2018-01-30 | 2018-02-28 | 2018-03-30 | 2018-04-30 | 2018-05-30 | 2018-06-30 | 2018-07-30 | 2018-08-30 | 2018-09-30 | 2018-10-30 | 2018-11-30 | 2018-12-30 | 2019-01-30 | 2019-02-28 | 2019-03-30 | 2019-04-30 | 2019-05-30
Invoice | 1510832.8173 | 815669.41 | 782039.0789 | 0 | 4097246.7956 | 801483.59 | 0 | 0 | 1623022.55 | 2709593.5251 | 1499571.2041 | 221587.4456 | 0 | 0 | 1379201.0038 | 826638.2585 | 2776583.7802 | 5462784.76 | 1090291.0498 | 1919376.5049 | 1461642.3602 | 3664619.6142 | -4028572.7482 | 6119200.5173 | - | - | - | - | -
Acc Invoice | 1510832.8173 | 2326502.2273 | 3108541.3061 | 3108541.3061 | 7205788.1017 | 8007271.6917 | 8007271.6917 | 8007271.6917 | 9630294.2417 | 12339887.7668 | 13839458.9709 | 14061046.4165 | 14061046.4165 | 14061046.4165 | 15440247.4203 | 16266885.6788 | 19043469.4591 | 24506254.2191 | 25596545.2689 | 27515921.7738 | 28977564.134 | 32642183.7482 | 28613611 | 34732811.5173
Certified | 1510832.8173 | 815669.415 | 575450.343 | 0 | 4021827.597 | 0 | 0 | -2648804.35 | 1623022.5542 | 2381902.5176 | 998040.429 | 0 | 0 | 0 | 704409.642 | 322273.2362 | 2776583.78 | 5062833.333 | 0 | 746712.14 | 2698526.538 | 2659364.1444 | 4364966.8681 | 4989568.9059 | - | - | - | - | -
Acc Certified | 1510832.8173 | 2326502.2323 | 2901952.5753 | 2901952.5753 | 6923780.1723 | 6923780.1723 | 6923780.1723 | 4274975.8223 | 5897998.3764 | 8279900.894 | 9277941.323 | 9277941.323 | 9277941.323 | 9277941.323 | 9982350.965 | 10304624.2012 | 13081207.9812 | 18144041.3142 | 18144041.3142 | 18890753.4542 | 21589279.9922 | 24248644.1367 | 28613611.0048 | 33603179.9107
Cashed | 4204461.15 | 0 | 1510832.8173 | 0 | 815669.415 | 575450.343 | 0 | 4021827.597 | 0 | -2648804.35 | 1623022.5542 | 0 | 2381902.5216 | 0 | 998040.429 | 0 | 704409.642 | 322273.2362 | 2776583.78 | 0 | 5062833.333 | 746712.14 | 0 | 2698526.538 | - | - | - | - | -
Acc Cashed | 4204461.15 | 4204461.15 | 5715293.9673 | 5715293.9673 | 6530963.3823 | 7106413.7253 | 7106413.7253 | 11128241.3223 | 11128241.3223 | 8479436.9723 | 10102459.5264 | 10102459.5264 | 12484362.048 | 12484362.048 | 13482402.477 | 13482402.477 | 14186812.119 | 14509085.3553 | 17285669.1353 | 17285669.1353 | 22348502.4683 | 23095214.6083 | 23095214.6083 | 25793741.1463
Cash Out
Month | 2017-01-30 | 2017-02-28 | 2017-03-30 | 2017-04-30 | 2017-05-30 | 2017-06-30 | 2017-07-30 | 2017-08-30 | 2017-09-30 | 2017-10-30 | 2017-11-30 | 2017-12-30 | 2018-01-30 | 2018-02-28 | 2018-03-30 | 2018-04-30 | 2018-05-30 | 2018-06-30 | 2018-07-30 | 2018-08-30 | 2018-09-30 | 2018-10-30 | 2018-11-30 | 2018-12-30 | 2019-01-30 | 2019-02-28 | 2019-03-30 | 2019-04-30 | 2019-05-30
Planned Cost | 2018-01-30: -12691897.7095; 2018-02-28: -1717599.8356; 2018-03-30: -1651255.1611; 2018-04-30: -1823649.4933; 2018-05-30: -1675216.577; 2018-06-30: -1666549.1706; 2018-07-30: -1649068.3409; 2018-08-30: -1654068.3409; 2018-09-30: -2330054.255; 2018-10-30: -2111645.835; 2018-11-30: -1449914.7274; 2018-12-30: -202163.1983
Acc Planned Cost | 2018-01-30: -12691897.7095; 2018-02-28: -14409497.5451; 2018-03-30: -16060752.7062; 2018-04-30: -17884402.1995; 2018-05-30: -19559618.7765; 2018-06-30: -21226167.9471; 2018-07-30: -22875236.288; 2018-08-30: -24529304.6289; 2018-09-30: -26859358.8839; 2018-10-30: -28971004.7189; 2018-11-30: -30420919.4463; 2018-12-30: -30623082.6446
Actual Cost | 2018-01-30: -14476821.6642; 2018-02-28: -464758.15; 2018-03-30: -636066.364; 2018-04-30: -227982.2; 2018-05-30: -1002543.7; 2018-06-30: -2079652; 2018-07-30: -1338133.11; 2018-08-30: -466468.93; 2018-09-30: -741229.8; 2018-10-30: -982193.99; 2018-11-30: -3339083.56; 2018-12-30: -3456805.66
Acc Actual Cost | 2018-01-30: -14476821.6642; 2018-02-28: -14941579.8142; 2018-03-30: -15577646.1782; 2018-04-30: -15805628.3782; 2018-05-30: -16808172.0782; 2018-06-30: -18887824.0782; 2018-07-30: -20225957.1882; 2018-08-30: -20692426.1182; 2018-09-30: -21433655.9182; 2018-10-30: -22415849.9082; 2018-11-30: -25754933.4682; 2018-12-30: -29211739.1282
EV | 2018-01-30: -1776865.6793; 2018-02-28: -2449614.5827; 2018-03-30: -3212150.5412; 2018-04-30: -4113412.5059; 2018-05-30: -5085500.8819; 2018-06-30: -6367850.3841; 2018-07-30: -12581379.9584; 2018-08-30: -14717582.7773; 2018-09-30: -17458583.2745; 2018-10-30: -20279703.3032; 2018-11-30: -21903062.0013; 2018-12-30: -22967311.9835
CV | 2018-01-30: 12699955.9849; 2018-02-28: 12491965.2315; 2018-03-30: 12365495.637; 2018-04-30: 11692215.8723; 2018-05-30: 11722671.1963; 2018-06-30: 12519973.6941; 2018-07-30: 7644577.2298; 2018-08-30: 5974843.3409; 2018-09-30: 3975072.6437; 2018-10-30: 2136146.605; 2018-11-30: 3851871.4669; 2018-12-30: 6244427.1447
SV | 2018-01-30: 10915032.0302; 2018-02-28: 11959882.9625; 2018-03-30: 12848602.165; 2018-04-30: 13770989.6936; 2018-05-30: 14474117.8946; 2018-06-30: 14858317.563; 2018-07-30: 10293856.3296; 2018-08-30: 9811721.8516; 2018-09-30: 9400775.6094; 2018-10-30: 8691301.4157; 2018-11-30: 8517857.445; 2018-12-30: 7655770.6612
CPI | 2018-01-30: 0.12274; 2018-02-28: 0.16395; 2018-03-30: 0.2062; 2018-04-30: 0.26025; 2018-05-30: 0.30256; 2018-06-30: 0.33714; 2018-07-30: 0.62204; 2018-08-30: 0.71125; 2018-09-30: 0.81454; 2018-10-30: 1.2; 2018-11-30: 0.85044; 2018-12-30: 0.78624
SPI | 2018-01-30: 0.14; 2018-02-28: 0.17; 2018-03-30: 0.2; 2018-04-30: 0.23; 2018-05-30: 0.26; 2018-06-30: 0.3; 2018-07-30: 0.55; 2018-08-30: 0.6; 2018-09-30: 0.8; 2018-10-30: 1.1; 2018-11-30: 0.72; 2018-12-30: 0.75
BAC | 2019-05-30: -33306177
EAC | 2019-05-30: -30665245.843
ETC | 2019-05-30: -1453506.7148
Note on C6: Author: to be read from the plan schedule %
Note on C7: Author: To be added manually from the monthly progress 4.5-J7
Note on C12: Author: To be taken manually on monthly basis from 4.4-P7
Note on C14: Author: taken monthly from 4.4 from all project summation 4.4- T7
Note on C16: Author: will be taken monthly from account
Note on B24: Author: budget cost for work performed(BCWP)
Note on B25: Author: cost variance (EV-AC)
Note on B26: Author: schedule variance (EV-PV)
Note on B27: Author: cost index (EV/AC)
Note on B28: Author: schedule index (EV/PV)
Note on B29: Author: budget at completion (contract budget)
Note on B30: Author: estimated cost at completion (BAC/CPI)